## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Bryan | David | Davith | Sandy | Trevor
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Parallel Tasks | Architecture |  |  |  |  | 2 |  | 2 | [5 empty] | 2
|  | Draft wireframe | UX/UI Designer | Sandy Yang (Trevor Poirier) | 2 |  | 2 |  |  |  |  | 2
| Requirements |  |  |  |  | 1 |  | 1 | [5 empty] | 5
|  | Review Commerce Bank Requirements | Project Manager & Developer | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1
| Documentation |  |  |  |  | 8 |  | 11 | [5 empty] | 54
|  | Project Charter | Project Manager & Developer | All | 2 |  | 4 |  | 4 | 4 | 4 | 4 | 4
|  | Requirements Document | Project Manager & Developer | All | 3 |  | 4 |  | 4 | 4 | 4 | 4 | 4
|  | Setup Document | Project Manager & Developer | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1
|  | Iteration 1 Report | Project Manager & Developer | All | 0.5 |  | 0.25 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
|  | Risk Management Report | Project Manager & Developer | All | 0.5 |  | 0.75 |  | 0.5 | 0.5 | 0.75 | 0.5 | 0.5
|  | Iteration 2 Report | Project Manager & Developer | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1
Iteration 1: | Development |  |  |  |  | 6.5 |  | 6.5 | [5 empty] | 20.5
|  | Research .NET | Project Manager & Developer | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1
|  | Install Visual Studio (with .NET plugins) | Project Manager & Developer | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1
|  | Install Google Cloud Platform | Database Admin | David Hoang (All) | 3 |  | 3 |  |  | 3
|  | Determine tools needed for project | Project Manager & Developer | All | 1 |  | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Set up Github repository branches | Project Manager & Developer | All | 0.5 |  | 1 |  | 1 | 1 | 1 | 1 | 1
| Analysis |  |  |  |  | 2 |  | 1.5 | [5 empty] | 7.5
|  | Prioritize time estimates in upcoming iteration | Project Manager | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1
|  | Identified needs for next iteration | Project Manager & Developer | All | 1 |  | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Iteration 2: | Design |  |  |  |  | 2 |  | 4 | [5 empty] | 6.5
|  | Table Structures | Project Manager & Database Admin | Davith(Bryan, David) | 1 |  | 1 |  | 0.5 | 0.5 | 1
|  | Database Chen Diagram | Project Manager & Database Admin | David(Bryan, Davith) | 1 |  | 3 |  | 1.5 | 1.5 | 1.5
| Development |  |  |  |  | 7.5 |  | 9.3 | [5 empty] | 9.25
|  | Added Required Fonts and Colors | UI/UX Designer | Sandy(Trevor) | 0.5 |  | 0.3 |  |  |  |  | 0.25
|  | Created an About Page | UI/UX Designer | Sandy(Trevor) | 1 |  | 3 |  |  |  |  | 3
|  | Created a Login Page | UI/UX Designer | Sandy(Trevor) | 1 |  | 1 |  |  |  |  | 1
|  | Added a Navigation Bar | UI/UX Designer | Sandy(Trevor) | 1 |  | 1 |  |  |  |  | 1
|  | Set up Microsoft Azure | Database Admin | David Hoang | 4 |  | 4 |  |  | 4
| Analysis |  |  |  |  | 3.5 |  | 3.5 | [5 empty] | 7.5
|  | Planned for upcoming demo for midterm | Project Manager & Developer | All | 2 |  | 2 |  |  |  | 1
|  | Identified risks for project development | Project Manager & Developer | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1
|  | Compared different Notification structures | Project Manager & Database Admin | Bryan(Davith, David) | 0.5 |  | 0.5 |  | 0.5 | 0.5 | 0.5
Iteration 3: | Design |  |  |  |  | 0 |  | 0 | [5 empty] | 0
| Development |  |  |  |  | 0 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 0 |  | 0 | [5 empty] | 0
Total |  |  |  |  | 32.5 | 32.5 | 94.5 | 38.8 | 20.25 | 27.25 | 22 | 25 |  | 94.5